## NCFS Checklist Draft Final
NCFS AGENCY END OF YEAR CHECKLIST FOR FISCAL YEAR END 2024 |  |  |  |  | For Agency Use
Task Group | Task | Task Description | Start Date | Complete By Date | Task Owner | Completion Status
Pre Year End Tasks
Pre Year End Tasks | Year-End memo & checklist distributed | Memo and checklist available on the OSC website. | 2024-05-13 | *** | *** | ***
Accounts Payable
Accounts Payable | Review open purchase orders and "Finally Close" purchase orders where no more receiving or invoicing will take place. | Agencies should begin to review all open purchase orders to determine if additional invoicing is pending and manually "Finally Close" purchase orders where no more receiving or invoicing is expected. PO lines that are not in a "Finally Closed" status will be carried forward to the next fiscal year. Agencies can use RPT-PO-001 PO Balance by Various COA Elements Report to review purchase order line status. | 2024-05-13 | 2024-06-28
Accounts Payable | Agencies should review Invoices incorrectly entered against future dated PO lines to manually Finally Close those POs. | Agencies should review Invoices incorrectly entered against future dated PO lines to manually close those POs. Agencies can find these invoices in the "Invoiced Future Year PO Lines" OTBI Report under the Accounts Payable reporting folder. POs in this scenario will fail PO Carry Forward. POs will need to be Finally Closed and re-created in eProcurement for any remaining PO balances. | 2024-05-13 | 2024-06-28
Accounts Payable | Year-end check run processed - all June manual payments entered | Last Check run for FY 2024 - PPR's must be submitted for approval by 10:25am Thursday, June 27th. Checks must be printed and confirmed by Thursday, 6/27 by 2:00pm. No additional June PPR's allowed after this date. | 2024-06-01 | 2024-06-27
Accounts Payable | Agencies may begin overriding payment terms on invoices or extend "Pay Through" dates on PPR's to pay invoices before June 27, where appropriate | Agencies may begin overriding payment terms to IMMEDIATE on invoices or extending their PPR "Pay Through" dates for all eligible payments to be issued in FY 2024 by June 27. All AP transactions to be paid from current year appropriations must be included in a PPR submitted to OSC for approval by 10:25am on June 27. Pcard invoices are treated as standard invoices in NCFS so please consider pcard payments in this process. | 2024-06-01 | 2024-06-27
Accounts Payable | Deadline for transfer of net proceeds from sale, lease or rental of lands | Supplier ID # for this transfer is 119133 - use the IGO site for your agency with the Alt Site Name 9000 OSC GEN FUND REV(OSCGENFUNDREV). Remittance message = FY2024 Net proceeds from Sale, Lease, Rental For those not processing through NCFS AP, submit an IC Transfer to Agency 9000 with your Budget Code and Remittance Info listed in the Notes field of the transfer. Submit for approval prior to 10:30 AM on 6/17/24. | 2024-06-01 | 2024-06-17
Accounts Payable | Deadline for transfer of funds for sale of surplus property | Supplier ID # for this transfer is 119133 - use the IGO site for your agency with the Alt Site Name 9000 OSC GEN FUND REV(OSCGENFUNDREV). Remittance message should be: FY2024 Sale of Surplus Property For those not processing through NCFS AP, prepare an NCFS IC Transfer to Agency 9000 with your Budget Code and Remittance Info listed in the Notes field of the transfer. Submit for approval prior to 10:30 AM on 6/17/24. | 2024-06-01 | 2024-06-17
Accounts Payable | Deadline for closing out travel advances | All permanent and temporary travel advances need to be closed. Travel advances account (52799000) must have a zero balance. RPT-EX-001 Employee Cash Advance Summary and Detail Report must show no open advances. Report should include parameters of Period From = Oct-23 and Period To = June 24. In the event of advance repayments, agencies should: 1) Receive and deposit re-payment from the employee. Deposit Journal Entry should CR the same COA used on the advance. This will clear the 52799000 travel advance account balance. 2) Create an Expense report for the amount of the re-payment/open advance using the same COA distribution as the advance. Payment of this expense report will close the open advance in NCFS without issuing payment to the employee. The payment of the expense report against the advance will have a $0.00 impact on the 532799000 account. | 2024-06-01 | 2024-06-21
Accounts Payable | Deadline for reviewing and resolving outstanding credit/debit memos | Resolve all credit/debit memos that have been outstanding for more than a year. Review all credit/debit memos for collection. Use Open Credit Memo Report RPT-AP-030 to review | 2024-06-01 | 2024-06-21
Accounts Payable | PO & Unpaid Invoice Carryforwards | No new Purchase Orders, PO change orders, or invoices keyed after 3:00pm June 28th | 2024-06-28 | 2024-07-02
Accounts Payable | Expense Reimbursements | No new Expense Reimbursements keyed after 3:00pm June 28th | 2024-06-28 | 2024-07-02
Accounts Payable | Begin flagging accruals | Agencies may begin flagging accruals for Accounts Payable invoices for Fiscal Year 2024. Accruals for unpaid invoices as of 6/30 will default to the accrual account set up on the supplier record. Accruals for invoices created 7/1 or after will require an accrual indicator to be tagged at the invoice line. All accrual entries should be completed and injected by 7/31. Additional documention will be sent from OSC about the accrual process in NCFS. (Pcard invoices or invoices with many lines may be updated by manual journal entry. Please see corresponding action item for manual accruals in General Ledger section.) | 2024-07-01 | 2024-07-31
General Ledger
General Ledger | Reimburse and close imprest cash accounts | Imprest cash should be reimbursed and closed out. Deposit remaining cash and record expenses via NCFS journal entry | 2024-06-01 | 2024-06-21
General Ledger | Review Journals Dashboard | Review all May and June Journals on the Requiring Attention, Incomplete, and Import Errors tabs and resolve issues | 2024-06-01 | 2024-06-27
General Ledger | Request to close Capital budget codes due to OSBM | https://www.osbm.nc.gov/capital-budget-code-closure-requestform/download?attachment |  | 2024-06-03
General Ledger | Capital Improvement Reports due to OSC | No Budget Revisions or Allotments for CIs should occur after reports are complete. |  | 2024-06-21
General Ledger | Review Journals - Resolve Rejected or Unposted Journals for May 2024 | Rejected Journals should be deleted or edited and resubmitted for approval. Ensure all Unposted Journals have been submitted for approval; Contact Dept of State Treasuer for WIRE or ACH Deposit Journals that need approval |  | 2024-06-27
General Ledger | Deadline for submitting May ACH & Wire Deposits for approval to DST | All May ACH & Wire Deposits must be submitted for approval to DST prior to 9:00 AM on June 27th. |  | 2024-06-27
General Ledger | Final Carryforward Request Due to OSBM | Carryforward guidance provided by OSBM - https://www.osbm.nc.gov/budget/budget-instructions/job-aids |  | 2024-06-28
General Ledger | Deadline for submitting May Disbursements for approval to OSC | All May Disbursements should be submitted for approval prior to 10:30 AM on June 28th. |  | 2024-06-28
General Ledger | Ensure all clearing accounts have a zero balance | Utilize Inquire on Detail Balances screen to ensure all clearing accounts have a zero balance before certification - 00001000, 00001100, 00004000, 00005000, 00002000, 00002100, 00006000, 00007000, 01000000, 02000000, 90000010, 90000050, 90000055, 90000011 |  | 2024-06-28
General Ledger | Ensure all suspense accounts have a zero balance | Utilize Inquire on Detail Balances screen to ensure all suspense accounts have a zero balance before certification - 51998000 & 51999000 |  | 2024-06-28
General Ledger | Review for incorrect journal categories used on Journal
General Ledger | EOY Trial Balances available for Fiscal Year Ended 2024 | Begin reviewing June 30 (13_Jun-24) trial balances NC Trial Balance by Agency and GASB Fund or Budget Code Report (RPTRTR011) | 2024-07-01 | 2024-08-30
General Ledger | Process manual reversing entries | Key and update any manual reversing entries. Review Prior Year 6/30 entries - determine if additional entries are needed | 2024-07-01 | 2024-07-26
General Ledger | Review Journals - Resolve Rejected or Unposted Journals for June 2024 | Rejected Journals should be deleted or edited and resubmitted for approval; Ensure all Unposted Journals have been submitted for approval; Contact Dept of State Treasurer for WIRE or ACH Deposit Journals that need approval |  | 2024-07-28
General Ledger | General fund Cash Carryforward | Carryforward guidance provided by OSBM - https://www.osbm.nc.gov/budget/budget-instructions/job-aids |  | Mid-July
General Ledger | Deadline for submitting June ACH & Wire Deposits for approval to DST | All June ACH & Wire Deposits must be submitted for approval to DST prior to 9:00 AM on July 29th. |  | 2024-07-29
General Ledger | Review 199xx Tax Budget Code manual Reversion entries in NCFS | FY 2024 reversion entries for tax budget codes (19901-19929 + 19949) entered by OSC. Agency effected: Department of Revenue |  | 2024-08-01
General Ledger | Review 199xx Non-Tax Budget Code manual Reversion entries in NCFS | FY 2024 reversion entries for non-tax budget codes (19950-19999) entered by OSC. Agencies effected: AOC, SOS, DST, DOL, DOR, DOI, DPS, DHHS, DOC, SBOE, OSC |  | 2024-08-01
General Ledger | Deadline for submitting June Disbursements for approval to OSC | All June Disbursements should be submitted for approval prior to 10:30 AM on July 31st. |  | 2024-07-31
General Ledger | FY 2024 Cash Close deadline | Post fourth quarter allotment reversion entry to NCFS with an effective date of June 30. |  | 2024-07-26
General Ledger | Record AP accruals; Record Items Received &Not Invoiced accruals | Agencies should review the Accounts Payable reports for June and July invoices and record enties as indicated in the reports. | 2024-07-01 | 2024-07-31
General Ledger | Cash Basis clearing account entries | Any June 30th entries that should be posted to the cash ledger such as adjustments to the funds held for other should be recorded. No June 30 entries should be posted to the cash account. | 2024-07-01 | 2024-07-31
General Ledger | Post manual accruals | Post manual accruals and adjustments for fiscal year ended June 30 in ACCRUAL ledger | 2024-07-01 | 2024-08-09
General Ledger | Post manual accruals | Post manual accruals and adjustments for fiscal year ended June 30 in MODIFIED ACCRUAL ledger | 2024-07-01 | 2024-08-12
General Ledger | Pcard Transaction Accruals | If an agency chooses to accrue pcard transactions with a journal entry rather than tagging each line of the invoice, agencies can use the RPT-AP-043 PCard Invoice Report to determine which transactions have a June purchase date and the corresponding amount for accrual. | 2024-07-01 | 2024-08-09
General Ledger | Deadline for pre-certifying final (June) budgetary reports | Certified June cash basis reports due to OSC by August 1st. NCFS Reversion entries post by 7/31. |  | 2024-08-01
Budget
Budget | Review & Reconcile IBIS Allotments, Budget Revisions & Appropriations for May 2024 | Ensure all budgetary entries are accounted for using NCFS Budget Reports. | 2024-06-01 | 2024-06-28
Budget | Capital allotment requests for June due to OSBM |  |  | 2024-06-03
Budget | Final CI Bond Requisition Due | Bond Requisition transfers posted in NCFS on Thursday, June 6th |  | 2024-06-05
Budget | Review & Reconcile IBIS Allotments, Budget Revisions & Appropriations for June 2024 | Ensure all budgetary entries are accounted for using NCFS Budget Reports. | 2024-07-01 | 2024-07-15
Budget | Complete budget closeout per OSBM guidance | https://www.osbm.nc.gov/budget/budget-instructions/budget-closeout
Intercompany
Intercompany | Process CI reversion transfer in NCFS | Supplier ID # for this transfer is 119133 - use the IGO site for your agency with the Alt Site Name 9000 OSC GEN FUND REV (OSCGENFUNDREV). Remittance message = FY2024 Reversions. For those not processing through the NCFS AP, prepare an NCFS IC Transfer to Agency 9000 with your Budget Code and Remittance Info listed in the Notes field of the transfer. Submit for approval prior to 10:30 AM on 6/17/24. |  | 2024-06-17
Intercompany | Review IC Transfers - Resolve Rejected or Incomplete Transfers for May 2024 | Rejected IC transfers no longer needed should be updated to 'Rejection Reviewed'; Incomplete IC Transfers should be completed or deleted, as applicable | 2024-06-01 | 2024-06-26
Intercompany | Deadline for submitting May Intercompany Transfers for approval to OSC | All May IC Transfers should be submitted for approval prior to 10:30 AM on June 27th. |  | 2024-06-26
Intercompany | Review IC Transfers - Resolve Rejected or Incomplete Transfers for June 2024 | Rejected IC transfers no longer needed should be updated to 'Rejection Reviewed'; Incomplete IC Transfers should be completed or deleted, as applicable | 2024-07-01 | 2024-07-28
Intercompany | Deadline for submitting June Intercompany Transfers for approval to OSC | All June IC Transfers should be submitted for approval prior to 10:30 AM on July 29th. |  | 2024-07-28
Projects & Grants
Projects & Grants | Reconcile 488 and 588 accounts | All 488 and 588 accounts must zero out. If there is a difference, correcting entries must be made. NC Federal Grant 488-588 Transfer Account Reconciliation Report (RPT-GM-016) | 2024-06-01 | 2024-07-25
Inventory
Inventory | Reconcile Cost Books (CASH, MOD ACCRUAL, ACCRUAL) | Reconcile all the cost books to ensure the adjustments perfomed in CASH reflects in Modified and Accrual Cost Books. Use these reports to assist in reconcilation. Scheduled Processes - Period Inventory Valuation Report - General Ledger Trial Balance Report - Account Analysis Report - Period Layer Inventory Valuation Report - General Ledger and Subledger Account Analysis Report - Costing Account Balances Report Inventory Reports -NC Valued Transaction Register Report (RPTIN004) -NC Expense Transactions and Exceptions Report (RPTIN021) | 2024-06-01 | 2024-06-28
Inventory | Reconcile Subledger (Cost) with GL | Reconcile Subledger (Cost) and GL by comparing Period end Inventory Valuation Report with General Ledger Trial Balance Report/Account Analysis Report | 2024-06-01 | 2024-06-28
Fixed Assets
Fixed Assets | Hold FY2025 Asset activity | No FY2025 asset transactions should be placed from 7/1 until 7/22 when the July period opens. Confirm the Depreciation period on your fixed assets dashboard shows Jul-24 before entering FY2025 data. | 2024-07-01
Fixed Assets | Review SBITA and Lease Asset Useful lives | Review your RTU Lease and SBITA assets on the NC SWCAP Assets Report (FA008) to verify the correct useful lives are used for these assets. Submit a help desk ticket (ncfs@ncosc.gov) to correct assets with incorrect lives by July 18th. Additional details can be found in https://www.osc.nc.gov/documents/files/fa-15-adding-rtu-asset-leased-asset |  | 2024-07-18
Fixed Assets | Fixed asset deadline | Last day to enter asset data for fiscal year is July 21. Year ending reports (Fixed Assets Outbound Interface to FCCS) is available. Agencies which miss this deadline should submit a help desk ticket to OSC |  | 2024-07-21
Fixed Assets | Fixed Assets clear exceptions | Clear all transfer, adjustment, and retirement exceptions by July 21 |  | 2024-07-21
Fixed Assets | Asset retirements completed for FY2024 | Retirements must be completed by the 7/21 deadline. OSC does not have the ability to backdate these transactions. |  | 2024-07-21
Fixed Assets | Asset transfers completed for FY2024 | Transfers must be completed by the 7/21 deadline. OSC does not have the ability to backdate these transactions. |  | 2024-07-21
Fixed Assets | Begin FY2025 asset activities | Asset transactions including additions, adjustments, transfers, and retirements for FY2025 assets can begin on July 22nd. |  | 2024-07-22
Accounts Receivable
Accounts Receivable | Identify accounts receivable accruals for journal entry and June 30 posting. | Receivable account to be entered on deposit line description. Accrual entries to be created and entered using the NC AGY REVERSING ACCR Journal Category. | 2024-07-01 | 2024-07-19
Financial Reporting
Financial Reporting | Year-end close packages | Prepare year-end close packages. | 2024-08-01 | 2024-08-30
Financial Reporting | Record Compensated Absence entries | Proprietary Funds Only: All compensated absence entries must be recorded in NCFS by this date. Notify OSC analyst if entries needed after this date. |  | 2024-08-05
Financial Reporting | Record GASB 68 Pension entries | Proprietary Funds Only: All GASB 68 Pension entries must be recorded in NCFS by this date. Notify OSC analyst if entries needed after this date. |  | 2024-08-05
Financial Reporting | Record GASB 75 OPEB entries | Proprietary Funds Only: All GASB 75 OPEB entries must be recorded in NCFS by this date. Notify OSC analyst if entries needed after this date. |  | 2024-08-05
Financial Reporting | Record Lease and SBITA Entries | All GASB Funds: All lease and SBITA related entries must be recorded in NCFS by this date. Notify OSC analyst if enteries needed after this date. |  | 2024-08-05
Financial Reporting | Review Annual Report information | Review GASB trial balances and DSS financial statements for completion and correctness. |  | 2024-08-10
Financial Reporting | Post 6/30 entries for transfer accounts | All 6/30 transfer related entries for accounts 48XXX and 58XXX must be complete by 8/12, including the matching of the interfund segment for every transfer line on NC GASB Transfers Reconciliation Report (RTR168), as needed . Notify OSC Financial Reporting analyst if entries are needed after 8/12. |  | 2024-08-12
Financial Reporting | Post 6/30 entries for due to/due from accounts | All 6/30 due to/due from entries should be completed by 8/12, including the matching of the interfund segment for every line on the NC GASB Due To and Due From Reconciliation Report (RTR169), as needed. Notify OSC Financial Reporting analyst if entries are needed after 8/12. |  | 2024-08-12
Financial Reporting | Annual Report Statements | Tier 1 - Agency financial statements due to OSC. |  | 2024-08-15
Financial Reporting | Annual Report Statements | Tier 2 - Agency financial statements due to OSC. |  | 2024-08-22
Financial Reporting | Annual Report Statements | Tier 3 - Agency financial statements due to OSC. |  | 2024-08-26
Financial Reporting | Annual Report Statements | All Others - Agency financial statements due to OSC. |  | 2024-08-29